BENKAS ENGINEERING

Benkas ERP

Complete Step-by-Step User Guide

Ramshy Bio Pvt. Ltd. — Ethanol Plant Construction Monitoring

Generated from the live site on 09 July 2026

This guide is generated by introspecting the running app, so its inventory and every field list are complete and always match the system.

# Contents

Right-click here and choose 'Update Field' to build the contents.

# 1.  What Benkas ERP is

Benkas ERP monitors the construction of the Ramshy Bio ethanol plant. It keeps five things honest and in one place:

PEOPLE — who came through the gate (staff, contractors, labour), attendance and manpower.

MATERIAL — what was requested, received (with weighbridge + invoice proof), quality-checked and consumed at site.

PROGRESS — each section's tasks, their % complete and the daily site log behind them.

SAFETY & ASSETS — permits, violations, generators and power.

GATE — the single scan point that feeds attendance and proves who was really on site.

## The daily rhythm

One simple loop runs every day:

| Step | What happens | Where |
| --- | --- | --- |
| 1. Gate scan | People scan IN (photo) and OUT at the Scan Station. | Gate Management |
| 2. Work | The section does its work; material is issued as needed. | site |
| 3. EOD log | The Incharge files the Daily Progress Log (task %, workers, material, photos) — from desk or phone. | Work Schedule |
| 4. Roll-up | Task % and section % update automatically; stock is issued. | automatic |
| 5. Read | PM & client read the dashboards and weekly reports. | Benkas MIS |

## How it all connects

(Shown as a text flow — this guide uses precise textual walkthroughs rather than screenshots so it can be regenerated from the live app without drift.)

GATE SCAN --> Gate Entry (who is on site) --> feeds --> Attendance & Manpower reports

|

'--> Daily Progress Log (EOD) --> writes --> Task %  --> rolls up --> Section %

|                                              |

|--> issues --> Stock Entry (material consumed) |

'--> photos + status ----------------> Section 360 / Benkas MIS

MATERIAL:  Material Request --> Purchase Receipt (GRN) --> Quality Inspection --> stock

'--> consumed in the Daily Progress Log

# 2.  The map — everything that exists

This inventory is generated from the live site, so it is complete.

## 2.1  Workspaces (sidebar order)

| # | Workspace | Purpose |
| --- | --- | --- |
| 1 | Gate Management | The gate's home — scanning, gate entries, passes, visitors, tools, vehicles and the gate registers. |
| 2 | Manpower Manager | Workforce masters, gate-driven attendance and manpower reports. |
| 3 | Material and Purchase | Requests, GRN receipts, quality, stock and material reports. |
| 4 | Work Schedule and Progress | Planning, the Daily Progress Log, Section 360 and progress reports. |
| 5 | Site Safety and Assets | Permits, violations, generators and power. |
| 6 | Benkas Core | The master data — sections, contractors, labour, activities, statuses. |
| 7 | Benkas MIS | The executive dashboard and the client weekly report. |

## 2.2  Doctypes (what each records)

### Benkas Core

| Doctype | What it records |
| --- | --- |
| Construction Activity | A standard build activity used to generate section tasks. |
| Contractor | A labour/works agency. |
| Delay Reason | Legacy delay-reason list. |
| Labour Master | A contract labourer (ID card prints here). |
| Plant Section | One plant area, its warehouse, WBS task and % complete. |
| Progress Status | The EOD status list (Work Done / stopped reasons) + colours. |

### Manpower

| Doctype | What it records |
| --- | --- |
| Gate Entry | One person's IN or OUT at a section. |

### Work Schedule

| Doctype | What it records |
| --- | --- |
| Daily Progress Log | THE end-of-day site log per section. |

### Site Safety Assets

| Doctype | What it records |
| --- | --- |
| Contractor Tools Register | Tools brought in and returned. |
| Electrical Work Permit | An electrical work permit (LOTO). |
| Gate Pass | Permission to leave site during the day. |
| Generator Log | A generator run. |
| Generator Master | A generator master. |
| Power Consumption Log | A phase/voltage reading. |
| Safety Violation Log | A logged safety breach. |
| Safety Work Permit | A high-risk work permit. |
| Site Vehicle | A site vehicle master. |
| Site Vehicle Log | A vehicle trip. |
| Visitor Log | A site visitor's sign-in/out. |

### Child tables (line-item grids inside the above)

Daily Material Consumed, Daily Progress Photo, Daily Task Progress, Daily Worker Log, Electrical Work Permit Job Log, Gate Entry PPE Item, Quality Inspection Photo, Safety Work Permit Worker.

## 2.3  Pages

| Page | What it does |
| --- | --- |
| Scan Station | The gate scan screen. |
| Section 360° | Everything about one section on one screen. |
| Section Task Planner | Set tentative task dates per section. |

## 2.4  Reports (the question each answers)

| Report | Answers |
| --- | --- |
| Contractor-wise Labour Count | How many labourers each contractor has, by skill and active status. |
| EOD Manpower MIS | How many people were on each section, by category, per day — with acknowledgement gaps. |
| Gate Register | Every in/out event across the whole site (people, visitors, vehicles, tools, gate passes, material trucks) in one timeline. |
| Generator Consumption MIS | Generator running hours, diesel and litres/hour per day. |
| Labour Attendance Register | Per-labourer daily in/out, hours and OT from gate scans. |
| Late Entry and OT Report | Who came in late and who did overtime. |
| Material Consumption by Item | Which items were consumed at site (from the daily log), by section. |
| Material Received vs Issued | Per section: material received vs issued value. |
| Material Section Stock Balance | On-hand quantity and value in each section's stores. |
| QC Rejection Report | Every rejected quality inspection with its reference. |
| Safety Violations Summary | Violations by section, type and person, with open counts. |
| Safety Violations by Contractor | Which contractor's people breach safety most. |
| Section Manpower & Work Log | Per section per day (last 30 days): workers, person-days and the actual work descriptions. |
| Section Progress - Planned vs Actual | Each section's task progress vs latest reported %. |
| Section WBS Progress | Every section activity with status, progress and planned dates. |
| Staff Attendance Summary | Staff attendance (from HRMS Attendance) — status, in/out, hours, late flag. |
| Stoppage Analysis | Stopped section-days by reason and by section/task across a week — this is where 'rain cost us 6 section-days' comes from. |
| Vehicle Utilisation | Trips, hours out and distance per site vehicle. |
| Visitor Register Summary | Visitor counts per section, distinct companies/visitors and who is still on site. |
| Weekly Section MIS | One summary row per section for the last 7 days — logs filed, latest %, open material requests. |
| Weekly Section Report | Pick a section + week and see everything: each task's latest %, status, days worked/stopped, the work narrative, person-days, material and photo count. |

## 2.5  Print formats (when each prints)

| Print format | Doctype | When it prints |
| --- | --- | --- |
| Contractor Tools Slip | Contractor Tools Register | When tools are logged in — TOOL- QR to scan out. |
| Daily Progress Report | Daily Progress Log | The full daily site log — tasks, workers, material, photos (A4). |
| Electrical Work Permit Print | Electrical Work Permit | The electrical permit with LOTO and job log (A4). |
| Gate Entry Slip | Gate Entry | After a gate IN — an 80mm thermal slip with the entry QR. |
| Gate Pass Slip | Gate Pass | For an approved gate pass — GP- QR for scan-out/return. |
| Labour ID Card | Labour Master | A labourer ID card — 80mm, photo + LAB- QR. |
| Material Request Slip | Material Request | A printable copy of a material request (A4). |
| Safety Work Permit Print | Safety Work Permit | The safety permit document with workers and photos (A4). |
| Staff ID Card | Employee | A staff ID card — 80mm, photo + EMP- QR. |
| Temporary Gate Slip | Gate Entry | For a one-day temp labourer — TMP- QR, valid the same day only. |
| Visitor Slip | Visitor Log | For a visitor — VIS- QR for sign-out. |

## 2.6  Where do I find X?

| I want to… | Workspace | Open |
| --- | --- | --- |
| Scan a person in/out | Gate Management | Scan Station |
| File the end-of-day log | Work Schedule and Progress | Daily Progress Log / PWA Daily EOD |
| Request material | Material and Purchase | Material Request |
| Receive a truck (GRN) | Material and Purchase | Purchase Receipt |
| See a section's full picture | Work Schedule / Benkas MIS | Section 360° |
| Plan task dates | Work Schedule and Progress | Section Task Planner |
| Log a safety violation | Site Safety and Assets | Safety Violation Log |
| Print an ID card | Manpower / Benkas Core | Employee / Labour Master → Print |
| The client weekly pack | Benkas MIS | Client Weekly MIS |
| Every gate event | Gate Management | Gate Register report |
| Why work stopped this week | Work Schedule / Benkas MIS | Stoppage Analysis |

# 3.  Gate Management

## What's on this workspace

The gate's home — scanning, gate entries, passes, visitors, tools, vehicles and the gate registers.

Charts: Benkas Entries by Category.

Shortcut tiles on this workspace:

| Tile | Type | Opens |
| --- | --- | --- |
| Scan Station | Page | benkas-scan |
| Gate Entry | DocType | Gate Entry |
| Temporary Passes | DocType | Gate Entry |
| Visitor Log | DocType | Visitor Log |
| Gate Pass | DocType | Gate Pass |
| Contractor Tools Register | DocType | Contractor Tools Register |
| Site Vehicle Log | DocType | Site Vehicle Log |
| Site Vehicle | DocType | Site Vehicle |
| Gate Register | Report | Gate Register |
| Visitor Register Summary | Report | Visitor Register Summary |
| EOD Manpower MIS | Report | EOD Manpower MIS |
| Labour Attendance Register | Report | Labour Attendance Register |
| Staff Attendance Summary | Report | Staff Attendance Summary |

## Pages, doctypes and reports on this workspace — one by one

### Page — Scan Station (Gate Scan Station)

The gate's home screen. A USB barcode scanner or the device camera reads a QR on an ID card / slip and the station does the right thing automatically — supermarket style. The input box is always focused so a USB scanner just works.

#### Step by step

Keep the page open at the gate. The scan box stays focused — a USB scanner types the code and hits Enter for you; or tap the camera button to scan with the device camera.

PERSON IN: scan an ID card (EMP-/LAB-/staff). The station finds the person, shows their PHOTO + name + contractor, pre-fills the section, opens the camera to snap a live IN photo, and creates the Gate Entry (In). A big banner confirms who and what.

PERSON OUT: scan the same card again — the station finds today's open IN and closes it (sets time-out). No typing.

TEMP PASS: tap 'Temp Pass' to quick-register a one-day labourer (or reuse a lost-card master) and print a Temporary Gate Slip (TMP- QR). Next day that slip is rejected as expired.

TOOLS IN: tap 'Tools In' to open the Contractor Tools Register and print a Contractor Tools Slip (TOOL- QR) for scanning out later.

GATE PASS: scan a Gate Pass Slip — if Approved it marks the person Out; scan again on return to mark Returned. A red 'PASS NOT APPROVED' means send them back to approve.

VISITOR: scan a Visitor Slip to sign the visitor out.

Read the RESULT BANNER after every scan (green = done, red = blocked, e.g. '…is Exited — ENTRY BLOCKED'). The recent-scans list shows the last events, each with a 'Print Slip' button.

### Gate Entry

The record of one person (staff, contractor or labour) entering or leaving a plant section. Normally created automatically by the Scan Station, but can be filled by hand. It is the source of truth for who was on site — attendance, manpower reports and the Daily Progress Log's worker check all read from it.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Person Type | Select | Yes | Is this a company Employee, a Contractor firm, or an individual Labour? |
| Person | Dynamic Link | Yes | Scan the ID card or pick the person entering the gate. |
| Plant Section | Link | Yes | Which plant area they are working in today. |
| Entry Type | Select | Yes | In when they arrive, Out when they leave. |
| Time In | Datetime | No | Pick date and time. |
| Time Out | Datetime | No | Pick date and time. |
| Manual Override Reason | Small Text | No | If you typed the time by hand instead of scanning, say why. |
| Vehicle No | Data | No | Type the value. |
| Gate Pass | Link | No | Pick a Gate Pass. |
| Temporary Pass | Check | Auto | Set when this entry was issued via a temporary gate slip (no pre-printed card). The temp slip works only for the day it was issued. |
| Work Description | Small Text | No | Type the value. |
| Gate Photo | Attach Image | Yes | Take a live photo at the gate to confirm who actually entered. |
| PPE Checklist | Table | No | Tick the safety gear the person is actually wearing before letting them in. |
| Acknowledgement Status | Select | No | Set by the Section Incharge once they confirm the person reported for work. |
| Dispute Remarks | Small Text | No | Type the value. |

#### Line items: Gate Entry PPE Item

| Column | Type | Required? | What to enter |
| --- | --- | --- | --- |
| PPE Item | Data | No | Type the value. |
| Available | Check | No | Tick if it applies. |

#### What happens on save / submit

Gate Entry is not submitted (workflows are off) — it saves as a record. For staff, a matching HRMS Employee Checkin is created so attendance is calculated. A QR key (EMP-/LAB-…) is stamped so the next scan finds it.

#### Common messages & what to do

| Message | What it means / what to do |
| --- | --- |
| Photo is mandatory | Every gate IN needs a live photo — snap it, or use 'Log IN without photo' only if the camera is broken. |
| No open entry to close | You scanned OUT for someone with no open IN today — they never scanned in, so there is nothing to close. |

Tip: Use the Scan Station for everyday gate work; open Gate Entry directly only to review or correct a record.

### Visitor Log

A site visitor with their company, host, purpose and photo. The gate signs them in and out.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Visitor Name | Data | Yes | Name of the person visiting. |
| Company | Data | No | Who they represent. |
| Purpose | Small Text | No | Why they are here. |
| Plant Section | Link | No | Pick a Plant Section. |
| Host Person | Link | No | The person or section they are here to see. |
| Time In | Datetime | No | Pick date and time. |
| Time Out | Datetime | No | Pick date and time. |
| Photo | Attach Image | No | Live photo of the visitor at the gate. |
| Visitor Slip | Barcode | No | Type the value. |
| Acknowledgement Status | Select | No | Choose one of: Pending, Confirmed, Disputed |

#### What happens on save / submit

Not submitted. Print the Visitor Slip (QR) for sign-out at the gate.

Tip: Visitors still on site (no time-out) show in the Visitor Register Summary.

### Gate Pass

Permission for a person to leave site during working hours (and return). The gate scans the pass out and back in.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Person Type | Select | Yes | Choose one of: Employee, Contractor, Labour Master |
| Person | Dynamic Link | Yes | Pick a person_type. |
| Plant Section | Link | No | Pick a Plant Section. |
| Reason | Small Text | No | Why the person needs to leave site during working hours. |
| Destination | Data | No | Where they are going. |
| Expected Out Time | Datetime | No | When they plan to leave. |
| Expected Return Time | Datetime | No | When they are expected back — used to flag overdue passes. |
| Actual Out Time | Datetime | No | Pick date and time. |
| Actual Return Time | Datetime | No | Pick date and time. |
| Pass Status | Select | No | Moves Requested → Approved → Out → Returned as the pass is used. |
| Barcode | Barcode | No | Type the value. |

#### What happens on save / submit

Not submitted. Pass Status moves Requested → Approved → Out → Returned; a scheduler flags passes as Overdue when the expected return time passes.

#### Common messages & what to do

| Message | What it means / what to do |
| --- | --- |
| PASS NOT APPROVED | The pass is still Requested — the person's Incharge must Approve it before they can leave. |

Tip: Print the Gate Pass Slip (QR) so the gate can scan it.

### Contractor Tools Register

Tools a contractor brings in, with quantity and photo. The gate scans them out and the returned quantity must match.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Contractor | Link | Yes | Pick a Contractor. |
| Tool Description | Small Text | No | Type the value. |
| Qty In | Int | No | Enter a number. |
| Qty Returned | Int | No | Enter a number. |
| Gate Entry In | Link | No | Pick a Gate Entry. |
| Gate Entry Out | Link | No | Pick a Gate Entry. |
| Status | Select | Auto | Choose one of: In, Returned, Mismatch |
| Photo | Attach Image | No | Attach a photo / file. |

#### What happens on save / submit

Status auto-flips In → Returned, or 'Mismatch' when the returned quantity differs from what came in.

Tip: A 'Mismatch' means hold the person and call the Incharge.

### Site Vehicle Log

A trip for a site vehicle — driver, purpose, out/in times and odometer.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Vehicle | Link | Yes | Pick a Site Vehicle. |
| Driver | Data | No | Type the value. |
| Plant Section | Link | No | Pick a Plant Section. |
| Purpose | Small Text | No | Type the value. |
| Time Out | Datetime | No | Pick date and time. |
| Time In | Datetime | No | Pick date and time. |
| Odometer Start | Float | No | Enter a number. |
| Odometer End | Float | No | Enter a number. |

#### What happens on save / submit

Not submitted. Feeds the Vehicle Utilisation report.

Tip: Fill odometer start/end to get distance in the report.

### Site Vehicle

A site vehicle — number, type, owner and driver.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Vehicle No | Data | Yes | Type the value. |
| Vehicle Type | Select | No | Choose one of: Jeep, Pickup, Forklift, Crane, Tempo, Two Wheeler, Other |
| Owner Type | Select | No | Choose one of: Company, Benkas, Contractor |
| Assigned Driver | Data | No | Type the value. |

#### What happens on save / submit

Saved as a master.

### Report — Gate Register

Every in/out event across the whole site (people, visitors, vehicles, tools, gate passes, material trucks) in one timeline.

How to read it: Date range + optional Type / Direction / Section / Contractor filters. Each row links back to its source record.

Type: Script Report · Based on: Gate Entry

### Report — Visitor Register Summary

Visitor counts per section, distinct companies/visitors and who is still on site.

How to read it: Still-On-Site = no time-out.

Type: Query Report · Based on: Visitor Log

### Report — EOD Manpower MIS

How many people were on each section, by category, per day — with acknowledgement gaps.

How to read it: Group by date + section + category.

Type: Query Report · Based on: Gate Entry

### Report — Labour Attendance Register

Per-labourer daily in/out, hours and OT from gate scans.

How to read it: One row per labourer per day.

Type: Query Report · Based on: Gate Entry

### Report — Staff Attendance Summary

Staff attendance (from HRMS Attendance) — status, in/out, hours, late flag.

How to read it: One row per employee per day.

Type: Query Report · Based on: Attendance

# 4.  Manpower Manager

## What's on this workspace

Workforce masters, gate-driven attendance and manpower reports.

Charts: Benkas Headcount by Section, Benkas Acknowledgement Status.

Shortcut tiles on this workspace:

| Tile | Type | Opens |
| --- | --- | --- |
| Gate Entry | DocType | Gate Entry |
| Gate Pass | DocType | Gate Pass |
| Employee | DocType | Employee |
| EOD Manpower MIS | Report | EOD Manpower MIS |
| Labour Attendance Register | Report | Labour Attendance Register |
| Staff Attendance Summary | Report | Staff Attendance Summary |
| Contractor-wise Labour Count | Report | Contractor-wise Labour Count |
| Late Entry and OT Report | Report | Late Entry and OT Report |

## Pages, doctypes and reports on this workspace — one by one

• Gate Entry — see its full chapter where it first appears.

• Gate Pass — see its full chapter where it first appears.

### Employee  (standard form)

Standard HRMS Employee — your permanent staff. Their gate scans create Employee Checkins and attendance.

#### Benkas additions to this standard form

This is the standard ERPNext/HRMS form. Benkas adds the fields below — fill these; the rest of the form works as usual.

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Grade | Link | No | Pick a Employee Grade. |
| Default Shift | Link | No | Pick a Shift Type. |
| Job Applicant | Link | No | Pick a Job Applicant. |
| Leave Approver | Link | No | Pick a User. |
| Employment Type | Link | No | Pick a Employment Type. |
| ID Card Barcode | Barcode | No | Type the value. |
| Expense Approver | Link | No | Pick a User. |
| Health Insurance No | Data | No | Type the value. |
| Payroll Cost Center | Link | No | Pick a Cost Center. |
| Shift Request Approver | Link | No | Pick a User. |
| Employee Advance Account | Link | No | Pick a Account. |
| Health Insurance Provider | Link | No | Pick a Employee Health Insurance. |
| PAN Number | Data | No | Type the value. |
| Provident Fund Account | Data | No | Type the value. |
| IFSC Code | Data | No | Type the value. |
| MICR Code | Data | No | Type the value. |

#### What happens on save / submit

Saved. A QR key (EMP-…) is stamped for the Scan Station.

Tip: Print the Staff ID Card (QR).

### Report — Contractor-wise Labour Count

How many labourers each contractor has, by skill and active status.

How to read it: One row per contractor.

Type: Query Report · Based on: Labour Master

### Report — Late Entry and OT Report

Who came in late and who did overtime.

How to read it: Late flag when first-in is after 09:00.

Type: Query Report · Based on: Gate Entry

# 5.  Material and Purchase

## What's on this workspace

Requests, GRN receipts, quality, stock and material reports.

Charts: Benkas Stock Movement by Purpose, Benkas QC Outcome.

Shortcut tiles on this workspace:

| Tile | Type | Opens |
| --- | --- | --- |
| Purchase Receipt | DocType | Purchase Receipt |
| Quality Inspection | DocType | Quality Inspection |
| Stock Entry | DocType | Stock Entry |
| Material Request | DocType | Material Request |
| Item | DocType | Item |
| Supplier | DocType | Supplier |
| Material Received vs Issued | Report | Material Received vs Issued |
| Material Section Stock Balance | Report | Material Section Stock Balance |
| Material Consumption by Item | Report | Material Consumption by Item |
| QC Rejection Report | Report | QC Rejection Report |

## Pages, doctypes and reports on this workspace — one by one

### Purchase Receipt  (standard form)

The Goods Receipt Note (GRN) — records material arriving at the gate from a supplier, with weighbridge readings and the mandatory supplier-invoice photo.

#### Benkas additions to this standard form

This is the standard ERPNext/HRMS form. Benkas adds the fields below — fill these; the rest of the form works as usual.

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Net Weight | Float | No | Enter a number. |
| Tare Weight | Float | No | Enter a number. |
| Gross Weight | Float | No | Enter a number. |
| Plant Section | Link | No | Pick a Plant Section. |
| Weighbridge Slip No | Data | No | Type the value. |
| Weight Variance | Check | Auto | Tick if it applies. |
| Supplier Invoice Photo | Attach Image | Yes | Attach a photo / file. |

#### What happens on save / submit

On Submit stock is added to the section warehouse. A large gap between the weighbridge net weight and the invoice quantity raises a Weight Variance flag for the Incharge to review.

#### Common messages & what to do

| Message | What it means / what to do |
| --- | --- |
| Invoice / delivery-challan photo is mandatory | The GRN will not save without the supplier document photo — it is your proof the material and paperwork arrived together. |

Tip: Fill the weighbridge slip number and gross/tare/net weights when a truck is weighed.

### Quality Inspection  (standard form)

The accept / reject / partial decision on received material, with photos of the goods. Standard ERPNext Quality Inspection.

#### Benkas additions to this standard form

This is the standard ERPNext/HRMS form. Benkas adds the fields below — fill these; the rest of the form works as usual.

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Inspection Photos | Table | No | Line items — add rows (Quality Inspection Photo). |

#### What happens on save / submit

A 'Rejected' inspection feeds the QC Rejection Report so bad material is tracked back to the supplier and the Purchase Receipt.

Tip: Attach at least one photo of the inspected material.

### Stock Entry  (standard form)

Standard stock movement. On this site you rarely open it by hand — the Daily Progress Log creates the Material Issue entries for you.

#### Benkas additions to this standard form

This is the standard ERPNext/HRMS form. Benkas adds the fields below — fill these; the rest of the form works as usual.

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Task | Link | No | Pick a Task. |
| Plant Section | Link | No | Pick a Plant Section. |

#### What happens on save / submit

Moves stock in/out of warehouses.

Tip: Look here to audit an auto-created Material Issue from a daily log.

### Material Request  (standard form)

A request for material to be issued to your section's work. Standard ERPNext Material Request, extended with Plant Section, Task and a Benkas status so it fits the site flow.

#### Benkas additions to this standard form

This is the standard ERPNext/HRMS form. Benkas adds the fields below — fill these; the rest of the form works as usual.

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Task | Link | No | Which sub-task this material is for (only tasks under the selected section). |
| Benkas Status | Select | Auto | Site issue-tracking status, driven by the daily site log — separate from ERPNext's own document status. |
| Plant Section | Link | Yes | Which plant area this material is requested for. |

#### What happens on save / submit

On Submit it becomes 'Requested'. After approval set the Benkas status to 'Approved'; the daily log then issues stock against it and moves it to Partially Issued / Issued. The PM closes it when done.

#### Common messages & what to do

| Message | What it means / what to do |
| --- | --- |
| Warehouse is mandatory for stock item | A stockable item needs the section warehouse on its row. |

Tip: Statuses: Requested → Approved → Partially Issued → Issued → Closed.

### Item  (standard form)

Standard ERPNext Item — the materials master.

Standard ERPNext/HRMS form — no Benkas-specific fields; use it as normal.

#### What happens on save / submit

Saved.

### Supplier  (standard form)

Standard ERPNext Supplier — material vendors.

Standard ERPNext/HRMS form — no Benkas-specific fields; use it as normal.

#### What happens on save / submit

Saved.

### Report — Material Received vs Issued

Per section: material received vs issued value.

How to read it: Compare Received Qty against Issued Qty/Value.

Type: Query Report · Based on: Stock Entry

### Report — Material Section Stock Balance

On-hand quantity and value in each section's stores.

How to read it: One row per section warehouse.

Type: Query Report · Based on: Plant Section

### Report — Material Consumption by Item

Which items were consumed at site (from the daily log), by section.

How to read it: Sorted by quantity consumed.

Type: Query Report · Based on: Daily Material Consumed

### Report — QC Rejection Report

Every rejected quality inspection with its reference.

How to read it: Trace a rejection back to the Purchase Receipt.

Type: Query Report · Based on: Quality Inspection

# 6.  Work Schedule and Progress

## What's on this workspace

Planning, the Daily Progress Log, Section 360 and progress reports.

Charts: Benkas Task Status.

Shortcut tiles on this workspace:

| Tile | Type | Opens |
| --- | --- | --- |
| Section 360° | Page | section-360 |
| Section Task Planner | Page | section-task-planner |
| Daily Progress Log | DocType | Daily Progress Log |
| Task | DocType | Task |
| Project | DocType | Project |
| Section Progress - Planned vs Actual | Report | Section Progress - Planned vs Actual |
| Section WBS Progress | Report | Section WBS Progress |
| Weekly Section Report | Report | Weekly Section Report |
| Stoppage Analysis | Report | Stoppage Analysis |
| Section Manpower & Work Log | Report | Section Manpower & Work Log |
| Weekly Section MIS | Report | Weekly Section MIS |

## Pages, doctypes and reports on this workspace — one by one

### Page — Section 360°

One screen that shows everything about a section: progress, the task checklist, manpower, material and recent activity. The PM can edit a task's % right here.

#### Step by step

Pick a section in the box at the top. The whole 360° view loads.

HEADER: section % complete, tasks done / total, how many tasks are Stopped, and an overall On-Track / Attention pill.

TASK CHECKLIST: every task with an editable % box (type a new number and it saves + rolls the section up), a coloured status chip (green = done, blue = in progress, red = stopped), the last work description, and the photos tagged to that task.

MANPOWER: on-site-today headcount, person-days (7-day and total), and breakdowns by category and contractor.

MATERIAL: consumed value, top items issued, and open material requests.

RECENT ACTIVITY: the last daily logs with photo, status and %.

### Page — Section Task Planner

Set the tentative start/end dates (and optional weight) for each activity in a section, so 'Delayed' can be detected and the client report has a schedule.

#### Step by step

Pick a section. Its activities load with any dates already set.

Either set a Section Start Date and click 'Re-fill dates from start' to cascade dates down the list by weight, or type each Tentative Start / Tentative End by hand.

Weight is optional — the section % works as a plain average if you leave weights at 0. If you use weights, the Total turns green at 1.00.

Click 'Save Plan'. You'll see 'Saved N tasks' and the dates persist.

Section Task Planner (live screenshot).

### Daily Progress Log

THE end-of-day site log — one per section per day. It captures what each task achieved (with a status and %), who worked, and what material was used. This is the single most important daily entry: everything on the dashboards flows from it.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Plant Section | Link | Yes | The plant area this day's log is for. |
| Log Date | Date | Yes | The date the work actually happened. |
| Incharge | Link | No | Defaults to you — the person responsible for this section today. |
| Auto Stock Entry | Link | Auto | Pick a Stock Entry. |
| No Work Today | Check | No | Tick if nothing happened here today — then just type the reason and submit. |
| Reason (no work) | Small Text | Sometimes | Why there was no work (holiday, full rain day, etc.). |
| Task Progress | Table | No | Line items — add rows (Daily Task Progress). |
| Workers Present | Table | No | Line items — add rows (Daily Worker Log). |
| Material Consumed | Table | No | Line items — add rows (Daily Material Consumed). |
| Photos | Table | No | Attach at least one site photo for the day (you don't need one per task). |
| Remarks | Small Text | No | Anything worth noting about the day. |
| Amended From | Link | Auto | Pick a Daily Progress Log. |

#### Line items: Daily Task Progress

| Column | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Task | Link | Yes | The specific sub-task worked on today (only tasks under this section are shown). |
| Status | Link | Yes | Work Done, Work in Progress, or one of the Stopped reasons. |
| % Complete | Percent | No | How complete this task is now, as a percentage (you type it). |
| Work Description | Small Text | Yes | What was actually done today — or, if stopped, why. At least 15 characters. |

#### Line items: Daily Worker Log

| Column | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Type | Select | Yes | Employee, Contractor or Labour. |
| Person | Dynamic Link | Yes | Who worked today. They must already have a gate entry for this section today, or the log won't save. |
| Task | Link | No | Which sub-task they worked on (optional). |
| Hours | Float | No | Hours worked. Defaults to 8 (a full day). |

#### Line items: Daily Material Consumed

| Column | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Item | Link | Yes | The material used from section stores. |
| Qty | Float | Yes | How much was used. |
| UOM | Link | No | Unit of measure (e.g. Nos, Kg, Bags). |
| Task | Link | No | Which sub-task it was used for. |
| Material Request | Link | No | Link the request this was issued against, if there was one. |
| No MR | Check | Auto | Ticked automatically if this item wasn't formally requested first — used for tracking, doesn't block the entry. |

#### Line items: Daily Progress Photo

| Column | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Image | Attach Image | No | Attach a photo / file. |
| Task | Link | No | Optional — tag the task this photo shows so photos group by task. |
| Caption | Data | No | Type the value. |

#### What happens on save / submit

On Submit the system does all of this for you, automatically:

• writes each task row's typed % onto the Task (last log of the day wins);

• recalculates the section's overall % complete;

• adds the worker hours as manpower-days onto each task;

• creates and submits ONE Stock Entry (Material Issue) for every material row, so stock drops — you never open Stock Entry yourself;

• if a material row was linked to a Material Request, moves that request to Partially Issued / Issued.

#### Common messages & what to do

| Message | What it means / what to do |
| --- | --- |
| Add at least one task row — or tick No Work Today | A working-day log needs at least one task row. If truly nothing happened, tick No Work Today and give a reason instead. |
| Row for <task>: describe the work in at least 15 characters | The Work Description is too short. Say what was actually done, or why it stopped. |
| Row for <task>: pick a status | Every task row needs a status (Work Done / Work in Progress / a Stopped reason). |
| Add at least one site photo for the day | At least one photo is required per log (not per task). Tick No Work Today to skip photos on an idle day. |
| <person> has no gate entry for this section today | You added a worker who never scanned in to this section today. Only people with a gate entry can be counted — deliberate, so manpower stays honest. |
| Heads up: <task> is marked stopped but its % went up | A friendly WARNING, not a block. A stopped task usually keeps the same %. |

Tip: On a phone, staff file this from the Benkas PWA 'Daily EOD' tile — same fields, same rules.

### Task  (standard form)

Standard Frappe Task — one activity under a section. Its % is set by the daily log or edited inline on Section 360. PMs can add/rename tasks under a section's parent task and they appear everywhere automatically.

#### Benkas additions to this standard form

This is the standard ERPNext/HRMS form. Benkas adds the fields below — fill these; the rest of the form works as usual.

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Total Expense Claim (via Expense Claim) | Currency | Auto | Enter a number. |
| Manpower Days Logged | Float | Auto | Enter a number. |
| Material Consumed Value | Currency | Auto | Enter a number. |

#### What happens on save / submit

Progress and status feed the section rollup and the WBS reports.

Tip: Plan tentative dates in the Section Task Planner.

### Project  (standard form)

Standard Frappe Project — the whole plant build. The 12 sections' parent tasks live under it.

#### Benkas additions to this standard form

This is the standard ERPNext/HRMS form. Benkas adds the fields below — fill these; the rest of the form works as usual.

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Total Expense Claim (via Expense Claims) | Currency | Auto | Enter a number. |

#### What happens on save / submit

Saved.

### Report — Section Progress - Planned vs Actual

Each section's task progress vs latest reported %.

How to read it: Compare Task Progress to Reported.

Type: Query Report · Based on: Daily Progress Log

### Report — Section WBS Progress

Every section activity with status, progress and planned dates.

How to read it: The full work-breakdown at a glance.

Type: Query Report · Based on: Task

### Report — Weekly Section Report

Pick a section + week and see everything: each task's latest %, status, days worked/stopped, the work narrative, person-days, material and photo count.

How to read it: Section + From/To date filters. The deep per-section view.

Type: Script Report · Based on: Daily Progress Log

### Report — Stoppage Analysis

Stopped section-days by reason and by section/task across a week — this is where 'rain cost us 6 section-days' comes from.

How to read it: Date range + optional section. Sorted by most stopped days.

Type: Script Report · Based on: Daily Progress Log

### Report — Section Manpower & Work Log

Per section per day (last 30 days): workers, person-days and the actual work descriptions.

How to read it: The narrative of what each section did.

Type: Query Report · Based on: Daily Progress Log

### Report — Weekly Section MIS

One summary row per section for the last 7 days — logs filed, latest %, open material requests.

How to read it: The weekly one-glance.

Type: Query Report · Based on: Daily Progress Log

# 7.  Site Safety and Assets

## What's on this workspace

Permits, violations, generators and power.

Charts: Benkas Violations by Section, Benkas Permit Status.

Shortcut tiles on this workspace:

| Tile | Type | Opens |
| --- | --- | --- |
| Safety Violation Log | DocType | Safety Violation Log |
| Safety Work Permit | DocType | Safety Work Permit |
| Electrical Work Permit | DocType | Electrical Work Permit |
| Generator Master | DocType | Generator Master |
| Generator Log | DocType | Generator Log |
| Power Consumption Log | DocType | Power Consumption Log |
| Safety Violations Summary | Report | Safety Violations Summary |
| Safety Violations by Contractor | Report | Safety Violations by Contractor |
| Generator Consumption MIS | Report | Generator Consumption MIS |
| Vehicle Utilisation | Report | Vehicle Utilisation |

## Pages, doctypes and reports on this workspace — one by one

### Safety Violation Log

A logged safety breach (no helmet, unsafe act…) with a mandatory photo and the corrective action taken. Feeds the safety reports and the exceptions page.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Violation Type | Select | Yes | What was seen (no helmet, no shoes, unsafe act, etc.). |
| Person Type | Select | No | Choose one of: Employee, Contractor, Labour Master |
| Person | Dynamic Link | No | Who committed the violation (leave blank if unknown). |
| Plant Section | Link | No | Pick a Plant Section. |
| Violation Datetime | Datetime | No | Pick date and time. |
| Photo | Attach Image | Yes | Photo evidence of the violation (required). |
| Corrective Action | Small Text | No | What was done about it on the spot. |
| Status | Select | No | Open until the issue is fixed, then set to Corrected. |

#### What happens on save / submit

Not submitted. An 'Open' violation shows on dashboards until you set it to 'Corrected'.

#### Common messages & what to do

| Message | What it means / what to do |
| --- | --- |
| Photo is mandatory | A violation must have a photo — it is the evidence. |

Tip: Repeat offenders roll up by contractor in the 'Safety Violations by Contractor' report.

### Safety Work Permit

A permit to do a high-risk job (hot work, height, confined space, excavation) with the workers involved and mandatory site/PPE photos.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Permit Type | Select | Yes | The kind of high-risk job (hot work, height, confined space, etc.). |
| Plant Section | Link | No | Pick a Plant Section. |
| Work Description | Small Text | No | Type the value. |
| Workers Involved | Table | No | Line items — add rows (Safety Work Permit Worker). |
| Valid From | Datetime | No | Start of the window this permit is valid for. |
| Valid To | Datetime | No | End of the validity window. |
| Issuing Incharge | Link | No | Pick a User. |
| Approving Incharge | Link | No | Pick a User. |
| Site/Area Photo | Attach Image | Yes | Photo of the work area before starting (required). |
| PPE-in-use Photo | Attach Image | Yes | Photo showing workers in the required safety gear (required). |
| Barricading/Fire-watch Photo | Attach Image | No | Photo of the barricading / fire-watch arrangement. |
| Permit Status | Select | No | Choose one of: Requested, Approved, Work in Progress, Closed |
| Closing Confirmation | Check | No | Tick only after you've physically checked the job is finished and the area is safe — required before the permit can be closed. |

#### Line items: Safety Work Permit Worker

| Column | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Worker Name | Data | No | Type the value. |
| Role | Data | No | Type the value. |

#### What happens on save / submit

Not submitted — the Permit Status field is set by hand for now (workflows are OFF; see the Admin appendix). A photo of the site area and PPE-in-use is mandatory.

#### Common messages & what to do

| Message | What it means / what to do |
| --- | --- |
| Site/Area photo and PPE-in-use photo are mandatory | A safety permit cannot be raised without both photos. |

Tip: Statuses run Requested → Approved → Work in Progress → Closed (set manually).

### Electrical Work Permit

A permit for electrical work, with LOTO (lock-out/tag-out) confirmation and a job log of start/stop and handover notes.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Job Description | Small Text | Yes | Type the value. |
| Plant Section | Link | No | Pick a Plant Section. |
| Equipment | Data | No | Type the value. |
| LOTO Confirmed | Check | No | Tick only after the equipment is locked out, tagged out and verified dead — required before this permit can be approved. |
| Valid From | Datetime | No | Pick date and time. |
| Valid To | Datetime | No | Pick date and time. |
| Issuing Engineer | Link | No | Pick a User. |
| Receiving Engineer | Link | No | Pick a User. |
| Job Log | Table | No | Record start/stop times and any hand-over during the job. |
| Permit Status | Select | No | Choose one of: Requested, Approved, Work in Progress, Closed |
| Closure Sign-off (Re-energized) | Check | No | Tick only after the equipment has been safely re-energized and handed back — required before closing. |

#### Line items: Electrical Work Permit Job Log

| Column | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Start Time | Datetime | No | Pick date and time. |
| End Time | Datetime | No | Pick date and time. |
| Handover Notes | Small Text | No | Type the value. |

#### What happens on save / submit

Not submitted — Permit Status set by hand for now. Tick LOTO Confirmed only when isolation is verified.

Tip: Close-out requires the 'Re-energized' sign-off tick.

### Generator Master

A generator on site — its ID, capacity and section.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Generator ID | Data | Yes | Type the value. |
| Capacity (kVA) | Data | No | Type the value. |
| Plant Section | Link | No | Pick a Plant Section. |

#### What happens on save / submit

Saved as a master.

### Generator Log

A generator run — start/stop, meter and diesel readings; running hours and consumption are computed.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Generator | Link | Yes | Pick a Generator Master. |
| Plant Section | Link | No | Pick a Plant Section. |
| Log Date | Date | No | Pick a date. |
| Shift | Select | No | Choose one of: Day, Night, General |
| Start Time | Datetime | No | Pick date and time. |
| Stop Time | Datetime | No | Pick date and time. |
| Running Hours | Float | Auto | Enter a number. |
| Opening Meter | Float | No | Enter a number. |
| Closing Meter | Float | No | Enter a number. |
| Diesel Filled (L) | Float | No | Enter a number. |
| Diesel Balance (L) | Float | No | Enter a number. |
| Consumption Rate (L/hr) | Float | Auto | Enter a number. |
| Fuel Slip Photo | Attach Image | No | Attach a photo / file. |

#### What happens on save / submit

Running hours and litres-per-hour are calculated on save from your times and meter readings.

Tip: Feeds the Generator Consumption MIS.

### Power Consumption Log

A phase-current and voltage reading for a section, per shift.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Log Date | Date | No | Pick a date. |
| Shift | Select | No | Choose one of: Day, Night, General |
| Plant Section | Link | No | Pick a Plant Section. |
| Reading By | Link | No | Pick a User. |
| R Phase (A) | Float | No | Enter a number. |
| Y Phase (A) | Float | No | Enter a number. |
| B Phase (A) | Float | No | Enter a number. |
| Voltage (V) | Float | No | Enter a number. |

#### What happens on save / submit

Saved as a reading.

Tip: Log by shift for trend tracking.

### Report — Safety Violations Summary

Violations by section, type and person, with open counts.

How to read it: Sorted by frequency.

Type: Query Report · Based on: Safety Violation Log

### Report — Safety Violations by Contractor

Which contractor's people breach safety most.

How to read it: Rolls violations up to the contractor.

Type: Query Report · Based on: Safety Violation Log

### Report — Generator Consumption MIS

Generator running hours, diesel and litres/hour per day.

How to read it: One row per generator per day.

Type: Query Report · Based on: Generator Log

### Report — Vehicle Utilisation

Trips, hours out and distance per site vehicle.

How to read it: One row per vehicle.

Type: Query Report · Based on: Site Vehicle Log

# 8.  Benkas Core

## What's on this workspace

The master data — sections, contractors, labour, activities, statuses.

Shortcut tiles on this workspace:

| Tile | Type | Opens |
| --- | --- | --- |
| Plant Section | DocType | Plant Section |
| Contractor | DocType | Contractor |
| Labour Master | DocType | Labour Master |
| Delay Reason | DocType | Delay Reason |
| Construction Activity | DocType | Construction Activity |

## Pages, doctypes and reports on this workspace — one by one

### Plant Section

One area of the plant (Distillation, Fermentation…). Each section links a Warehouse, a parent Project Task (its WBS) and a Cost Center, and carries the rolled-up section % complete.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Section Name | Data | Yes | Type the value. |
| Section Code | Data | Yes | Type the value. |
| Is Active | Check | No | Tick if it applies. |
| Section % Complete | Percent | Auto | Enter a number. |
| Section Start Date | Date | No | Planned start of work in this section — anchors the tentative task dates. |
| Warehouse | Link | No | Pick a Warehouse. |
| Project Task | Link | No | Pick a Task. |
| Cost Center | Link | No | Pick a Cost Center. |
| Incharge | Link | No | Pick a User. |

#### What happens on save / submit

Saved as a master. Its Project Task holds the section's activity sub-tasks.

Tip: The 12 sections are seeded — you rarely add new ones.

### Contractor

A labour/works agency — licence, agreement validity, contact and linked Supplier. Labour and billing group under the contractor.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Agency Name | Data | Yes | Type the value. |
| Registration No | Data | No | Type the value. |
| Labour License No | Data | No | Type the value. |
| Agreement Valid Upto | Date | No | Pick a date. |
| Contact Person | Data | No | Type the value. |
| Phone | Data | No | Type the value. |
| Linked Supplier | Link | No | Pick a Supplier. |

#### What happens on save / submit

Saved as a master.

Tip: Set Agreement Valid Upto so expiries can be tracked.

### Labour Master

A contract labourer's record — name, contractor, category, ID proof and photo. The QR ID card prints from here.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Labour Name | Data | Yes | Type the value. |
| Contractor | Link | No | Pick a Contractor. |
| Category | Select | No | Choose one of: Skilled, Semi-skilled, Unskilled |
| Status | Select | No | Choose one of: Active, Inactive, Exited |
| ID Proof Type | Select | No | Choose one of: Aadhaar, PAN, Voter ID, Driving License, Other |
| ID Proof No | Data | No | Type the value. |
| Photo | Attach Image | No | Attach a photo / file. |
| ID Card Barcode | Barcode | No | Type the value. |

#### What happens on save / submit

A QR key (LAB-…) is stamped for the Scan Station. An 'Inactive'/'Exited' labourer is blocked at the gate.

Tip: Print the Labour ID Card (80mm thermal, with photo + QR).

### Delay Reason

A short master list of delay reasons (kept for reference/history).

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Reason | Data | Yes | Type the value. |

#### What happens on save / submit

Saved as a master.

Tip: Day-to-day stoppages are now captured by the task Status; this list is legacy.

### Construction Activity

A standard activity in the build sequence (Civil → Erection → … → Commissioning) with a default duration and weight. Used to generate each section's task list.

#### Fields — what to enter

| Field | Type | Required? | What to enter |
| --- | --- | --- | --- |
| Activity Name | Data | Yes | Type the value. |
| Sequence | Int | No | Enter a number. |
| Default Weight % | Percent | No | Enter a number. |
| Default Duration (days) | Int | No | Used to pre-fill tentative task dates (start + cumulative durations). |
| Is Active | Check | No | Tick if it applies. |

#### What happens on save / submit

Saved as a master. Running the WBS generator creates these activities as sub-tasks under every section.

Tip: See the Admin appendix to regenerate section tasks after changing activities.

# 9.  Benkas MIS

## What's on this workspace

The executive dashboard and the client weekly report.

Charts: Benkas Headcount by Section, Benkas Violations by Section.

Shortcut tiles on this workspace:

| Tile | Type | Opens |
| --- | --- | --- |
| Section 360° | Page | section-360 |
| Section Task Planner | Page | section-task-planner |
| Setup / Masters | URL | /app/benkas-core |

## Pages, doctypes and reports on this workspace — one by one

## Client Weekly MIS pack — how to produce it

The client-facing weekly report (cover scorecard, section-wise table, per-section detail, manpower & material annexes, stoppage & exceptions) builds automatically every week and lands in the BENKAS PM folder and the app's docs/. To build one on demand:

bench --site <site> execute benkas_erp.setup.client_mis.build

Or for a specific week ending:

bench --site <site> execute benkas_erp.setup.client_mis.build --kwargs "{'week_ending':'2026-07-06'}"

# 10.  Daily / weekly routine — one page per role

## Gate Security

| When | Do this |
| --- | --- |
| Morning | Scan every person/vehicle in and out at the Scan Station; snap IN photos; issue temp slips and tool slips; sign visitors out. |
| During the day | — |
| Evening / weekly | Hand over the gate; make sure every open IN has been closed. |

## Section Incharge

| When | Do this |
| --- | --- |
| Morning | Acknowledge your section's gate entries (bell); raise Material Requests. |
| During the day | Supervise work; keep Safety Violation Log current. |
| Evening / weekly | File the Daily Progress Log (EOD) — task rows with status/%/description, workers, material, photos; or tick No Work Today. On a phone use the PWA 'Daily EOD' tile. |

## Stores / Weighbridge

| When | Do this |
| --- | --- |
| Morning | Receive trucks: create the Purchase Receipt (GRN) with weighbridge weights and the mandatory invoice photo. |
| During the day | Run Quality Inspection on received material. |
| Evening / weekly | Reconcile Material Received vs Issued. |

## Safety Officer

| When | Do this |
| --- | --- |
| Morning | Issue Safety / Electrical Work Permits with photos. |
| During the day | Log every Safety Violation with a photo and corrective action. |
| Evening / weekly | Review open violations on the dashboard. |

## Project Manager

| When | Do this |
| --- | --- |
| Morning | Scan the MIS dashboard and EOD compliance (which sections filed today). |
| During the day | Edit task % on Section 360; plan dates in the Task Planner; approve material requests. |
| Evening / weekly | Generate / read the Weekly Section Report, Stoppage Analysis and the Client Weekly MIS pack. |

## Ramshy Bio Management

| When | Do this |
| --- | --- |
| Morning | Open Benkas MIS for the executive dashboard. |
| During the day | — |
| Evening / weekly | Read the Client Weekly MIS pack. |

# 11.  Troubleshooting & FAQ

Q1. A person's photo won't upload / the camera is blank at the gate.

Use 'Log IN without photo' so the queue isn't held up, then check the browser's camera permission and lighting. The live photo is your dispute proof, so fix the camera soon.

Q2. The Scan Station says 'ENTRY BLOCKED (… is Exited/Inactive)'.

That ID card is deactivated. Refuse entry and send the person to their Incharge / the PM.

Q3. The Scan Station shows red 'PASS NOT APPROVED'.

The gate pass is still Requested. Send the person back to their Incharge to Approve it.

Q4. A temp slip is rejected the next morning as 'EXPIRED TEMP SLIP'.

Temporary Gate Slips are valid the same day only. Issue a fresh temp slip.

Q5. Tools show 'Mismatch' when scanning out.

The returned quantity doesn't match what came in. Hold the person and call the Incharge.

Q6. My Daily Progress Log won't save: 'Add at least one task row'.

A working-day log needs at least one task row. If nothing happened, tick 'No Work Today' and type a reason.

Q7. 'describe the work in at least 15 characters'.

The Work Description is too short — say what was done, or why it stopped (15+ characters).

Q8. '<person> has no gate entry for this section today'.

You added a worker who never scanned in to this section today. Only people with a gate entry can be counted — this keeps manpower honest.

Q9. A task is marked stopped but I get a 'went up' warning.

It's only a warning, not a block. A stopped task normally keeps the same %; adjust if you really moved work, otherwise leave it and submit.

Q10. What are the EOD statuses and which count as a stoppage?

Work Done, Work in Progress, and five 'Stopped —' reasons. Any status ticked 'Is a Stoppage' in the Progress Status master feeds the Stoppage Analysis report.

Q11. How do I file the EOD from my phone?

Open the Benkas PWA, tap 'Daily EOD', pick the section, add task rows (task/status/%/description), snap photos, submit. Same rules as the desk.

Q12. The section % isn't updating.

Section % comes from the Daily Progress Log task rows ON SUBMIT. Make sure the log was submitted (not left as a draft), or edit the task % directly on Section 360.

Q13. Dates I set in the Task Planner disappear after saving.

Fixed — they now display correctly. If you're on an older build, pull the latest and run bench build + clear-cache.

Q14. Slips print too big / not on the thermal roll.

Gate/ID slips are formatted for an 80mm thermal roll; the DPR and Material Request are A4. Pick the matching printer.

Q15. Where do I print an ID card?

Open the Employee (Staff ID Card) or Labour Master (Labour ID Card) and Print — both are 80mm with photo + QR.

Q16. The GRN won't save.

The supplier invoice / delivery-challan photo is mandatory on the Purchase Receipt.

Q17. What is the Weight Variance flag?

When the weighbridge net weight differs a lot from the invoice quantity, the GRN flags it for the Incharge to review; it also appears in the weekly exceptions.

Q18. Why can't I submit a Safety/Electrical Permit through a workflow?

Approval workflows are currently OFF (see the Admin appendix). For now set the Permit Status field by hand. They'll be switched on at go-live.

Q19. Who receives a notification and when?

Section Incharges get a bell alert when someone scans into their section; approval and status-change alerts follow the configured Notifications.

Q20. How do I add a new task to a section?

Open Task, set its Parent Task to the section's Project Task. It then shows in Section 360, the Task Planner, the daily log dropdown and the WBS reports automatically.

Q21. How do I regenerate a section's activity tasks?

See the Admin appendix — the WBS generator recreates the standard activities under each section (idempotent).

Q22. How do I produce the client's weekly report?

It builds automatically every week, or run it on demand (Admin appendix). It lands in the BENKAS PM folder and the app's docs/.

Q23. A report opens empty.

Most reports default to a recent date window — widen the From/To dates. Section-scoped reports need data logged for that section in the window.

Q24. What does 'Attention' vs 'On Track' mean on Section 360?

'Attention' shows when any task in the section is currently in a Stopped status; otherwise 'On Track'.

Q25. Can two people file the same section's EOD on the same day?

Yes, but the last submitted log wins for each task's %. Agree who files to avoid confusion.

# 12.  Admin appendix (for future-you)

## Regenerate this guide & the other docs

This guide: bench --site <site> execute benkas_erp.setup.userguide.build

System documentation: benkas_erp.setup.docgen.build

Role quick-refs: benkas_erp.setup.usermanual.build_all

Client weekly pack: benkas_erp.setup.client_mis.build

## Reseed / regenerate data

Masters + 12 sections + WBS tasks: benkas_erp.setup.seed.run (idempotent).

Progress Status list only: benkas_erp.setup.seed.seed_progress_statuses.

Regenerate section activity tasks: benkas_erp.setup.activities.generate_section_tasks.

Demo/UAT data: benkas_erp.setup.demo_data.reset then .run.

Full health check: benkas_erp.setup.audit.run (expect 0 FAIL).

## Deferred go-live items (not yet on)

Approval WORKFLOWS are OFF (WORKFLOWS_ACTIVE=False). Permit/request statuses are set by hand for now; flip the flag + migrate to enforce approvals at go-live.

USER PERMISSIONS: restrict each Section Incharge to their own Plant Section — to be applied on the real site.

required_apps (erpnext, hrms) is set; complete the ERPNext setup wizard before seeding on a fresh site.

— End of guide —  Generated by Benkas ERP on 09 Jul 2026