Benkas ERP

User & Operations Manual

Ramshy Bio Pvt. Ltd. — Ethanol Plant  |  Version 1.0  |  06 Jul 2026

# Getting started

Benkas ERP is the system Benkas Engineering uses to run and monitor the Ramshy Bio ethanol-plant construction — who is on site, what material moved, how each section is progressing, and site safety. This manual walks each role through their real day, step by step.

## Logging in

Open the site in a browser (your supervisor will give you the address, e.g. the plant server or the Frappe Cloud link).

Enter your username (usually your email) and password. If you don't have a login, ask the Benkas Project Manager to create one and assign your role.

After login you land on the app screen. Tap the Benkas ERP tile for the dashboard, or Benkas Core for master setup. Your role decides which screens you can see.

Roles: Gate Security, Section Incharge, Stores/Weighbridge Operator, Safety Officer, Generator/Electrical Operator, Benkas Project Manager, and Ramshy Bio Management. You only see what your role needs.

# 1.  Gate Security — your day

You are the front door of the plant. Almost everything you do is a scan. Keep the Scan Station open all day.

## Morning setup

Log in and open the Scan Station: go to /app/benkas-scan (bookmark it). You'll see one big input box and a large status panel.

Plug in the USB barcode scanner. It behaves like a keyboard — it types the code and presses Enter for you. Do NOT click anywhere; the input box stays focused on its own.

Optional: if you're on a tablet with no USB scanner, use the '📷 Camera scan' button instead (works in Chrome/Edge).

## Scanning a person IN

Person shows their ID card. Scan the QR.

The screen instantly shows their PHOTO, name and contractor. Look at the photo and confirm it's the same person standing in front of you.

The section they usually work in is pre-filled. Change it only if they're working somewhere else today.

The camera preview opens. Tap '📸 Snap & Log IN' to capture their live photo and record the entry. That's it — zero typing.

If the camera isn't available, tap 'Log IN without photo' (use only if you must).

Why the photo: The live gate photo proves who actually entered today, next to their card photo. It is what protects you if there's ever a dispute about who was on site.

## Scanning the same person OUT

When they leave, scan the same card again.

The system finds their open entry for today and closes it — big green 'OUT RECORDED'. No photo, no typing.

## Someone has no card / a blocked card

No card yet: send them to the Benkas PM to be registered and issued a card. Do not let unregistered people wander in.

Red 'ENTRY BLOCKED' (labour is Inactive/Exited): their contract ended or they were deactivated. Do not allow entry — send them to their Incharge or the PM.

'Not found': the card is damaged or from another site. Send them to the PM for a re-issue.

## Material vehicle arrival

When a supplier truck arrives with material, that's the Stores/Weighbridge Operator's GRN process (Chapter 3). Your job: note the vehicle, direct it to the weighbridge, and let the stores operator take over.

## Visitor arrival + slip

Create a new Visitor Log: fill visitor name, company, purpose, who they're visiting (host), and the section. Take their photo.

Save. Print the Visitor Slip (Print → Visitor Slip) and hand it to the visitor — it carries a QR.

When the visitor leaves, scan the slip at the Scan Station → the log closes automatically ('VISITOR OUT').

## Contractor tools in

When a contractor brings tools, open a new Contractor Tools Register: contractor, tool description, quantity, photo.

At exit, verify the tools leaving match what came in. The system flags a Mismatch if returned quantity differs — hold the person and call the Incharge.

## Gate Pass verification at exit

Anyone leaving during working hours must show a Gate Pass. Scan its QR.

GREEN 'GATE PASS — OUT': approved, let them go; the time is recorded.

RED 'PASS NOT APPROVED': do NOT let them out. Send them back to their Incharge to get the pass approved.

On return, scan again → 'RETURNED'. This closes the loop so no one is marked as still-out overnight.

## End of day

Scan out anyone still inside as they leave.

Any gate pass left 'Out' past its return time turns 'Overdue' automatically and shows on the manpower report — flag those to the PM.

## Error messages — what they mean

| Message on screen | What to do |
| --- | --- |
| ENTRY BLOCKED (…is Exited/Inactive) | Card deactivated — refuse entry, send to Incharge/PM. |
| PASS NOT APPROVED | Send the person back to their Incharge to approve the gate pass. |
| Visitor already signed out | The slip was already scanned out — no action needed. |
| Gate pass already returned | Loop already closed — no action needed. |
| … not found | Damaged/foreign card — send to PM for re-issue. |
| Unrecognised code | That QR isn't a Benkas card/slip — ignore. |

# 2.  Section Incharge — your day

You own one plant section. You confirm who really worked, log the day's progress, request material, and keep your section safe.

## Morning: acknowledge gate entries

Open your notifications (bell icon) — each person logged into your section this morning raises a pending acknowledgement.

Open the Gate Entry list filtered to your section, status 'Pending'.

For each: if the person actually reported to you and the work matches, click 'Confirm'. If they never showed up or were redirected, click 'Dispute' and add a remark.

Why: Confirmed vs Disputed is what makes contractor-labour billing honest — you're signing that the person was really there.

## Raising a Material Request

New Material Request. Set type = 'Material Issue' (material going out to your work).

Fill Plant Section (yours) and the Task it's for, then add item lines with quantity.

Submit. It goes to 'Requested'. Once approved it becomes 'Approved' and can be issued against by the daily log.

## The Daily Progress Log (your main job)

One log per section per day captures everything: task progress, who worked, and material used. When you submit it, the system updates task %, section %, and issues the material automatically.

New Daily Progress Log. Section and date are pre-set; you are the Incharge.

Task Progress table: add a row per sub-task worked on. Pick the task (only tasks under your section show), set % complete, write one line of activity, and a Delay Reason only if it fell behind.

Workers Present table: add each person who worked, their task and hours (default 8). Note: a worker who has no gate entry for your section today CANNOT be added — the log will refuse to save with a clear message. That's deliberate: only people who actually came through the gate count.

Material Consumed table: add item, quantity, unit, task, and (if it was requested) link the Material Request. Leave the request blank if there wasn't one — it's just flagged 'No MR' for visibility, it won't block you.

Site Photos: attach at least one photo of the day's work (required).

Submit.

What happens automatically on submit:

Each task's % is updated from your Task Progress rows.

One Stock Entry (Material Issue) is created and submitted for all your material rows — stock drops automatically. You never touch Stock Entry.

If a Material Request was linked, its status moves to Partially Issued or Issued.

Manpower-days and material value are added onto the tasks; your section % is recalculated and flows to the dashboard.

## Logging a safety violation

New Safety Violation Log. Pick the violation type, the person, your section.

Attach a photo (required) and note the corrective action taken.

Leave status 'Open' until fixed, then set 'Corrected'.

## Approving gate passes

When someone in your section needs to step out, they (or you) raise a Gate Pass. Open it and click 'Approve'. Only then will the gate let them out. Your login + the timestamp is the authorised signature.

# 3.  Stores / Weighbridge Operator — your day

## Receiving material (gate to stores)

Truck arrives → weighbridge. Note gross and tare weight.

New Purchase Receipt (GRN): supplier, item, quantity, the section warehouse it's going to, and the weighbridge fields (gross/tare — net is worked out).

Upload the supplier invoice / delivery-challan photo. This is MANDATORY — the GRN will not save without it. That photo is your proof the material and paperwork matched at the gate.

If net weight differs from the ordered quantity by more than a little, the system sets a 'Weight Variance' flag for the Incharge to review.

Save. For items that need inspection, a Quality Inspection is required before the material is accepted (Chapter 4 / the Safety-and-quality flow).

## Issuing against a Material Request

You normally don't issue material by hand — the Section Incharge's Daily Progress Log issues it automatically against their Material Request. Your job is to keep stock accurate: make sure every GRN is entered so the section warehouse balance is right. Check the 'Material Section Stock Balance' report anytime.

## Quality inspection handoff

Items flagged 'inspection required' force a Quality Inspection before the GRN can be completed.

The Benkas Incharge records Accept / Reject / Partial and can attach photos of the material condition.

Rejected material shows on the 'QC Rejection Report'.

# 4.  Safety Officer — your day

## Work permits lifecycle

High-risk jobs (hot work, height, confined space, excavation, electrical) need a permit before work starts.

New Safety Work Permit (or Electrical Work Permit). Set the permit type, section, work description, workers involved, and the validity window.

Attach the mandatory photos: site/area photo and PPE-in-use photo (and barricading where relevant). The permit won't progress without them.

Approve → the state moves Requested → Approved.

When work starts, move it to 'Work in Progress'.

To Close: you must tick 'Closing Confirmation' — that means you have physically checked the job is finished and the area is safe. Only then can it be closed. For electrical permits, LOTO must be confirmed before approval and the re-energized sign-off before closing.

## Violation log & PPE review

Maintain the Safety Violation Log (photo mandatory). Repeat offenders by contractor show on the 'Safety Violations by Contractor' report — use it in contractor reviews.

Gate entries carry a PPE checklist the guard ticks; spot-check compliance.

# 5.  Benkas Project Manager — your day

## Master data

Plant Sections, Contractors, Labour, Delay Reasons, Construction Activities live in the Benkas Core workspace.

Issue/re-issue ID cards from Employee and Labour Master (Print → ID Card). Deactivating a Labour (status Inactive/Exited) instantly blocks their card at the gate.

## Adding a new Plant Section and its tasks

Create the Plant Section (a Warehouse, Task and Cost Center get wired to it during seeding; for a brand-new one set these links).

To break the section into standard construction activities (civil, erection, wiring, installation, testing, commissioning…), run the WBS generator: it creates a sub-task per active Construction Activity under the section's task.

Edit the Construction Activity master to add/remove activities, then regenerate to pick up new ones.

Command: Regenerate WBS sub-tasks with benkas_erp.setup.activities.generate_section_tasks (or the full setup_activities).

## Reports

Every workspace carries its reports. The full list:

| Report | Answers |
| --- | --- |
| EOD Manpower MIS | Headcount by section & category, ack reconciliation. |
| Contractor-wise Labour Count | How many labour each contractor has, by skill. |
| Late Entry and OT Report | First-in / last-out and late arrivals. |
| Material Received vs Issued | Section-wise received vs issued quantity/value. |
| Material Section Stock Balance | On-hand stock per section warehouse. |
| QC Rejection Report | Rejected quality inspections. |
| Section Progress - Planned vs Actual | Task progress vs reported progress. |
| Section WBS Progress | Every activity sub-task's status & %. |
| Delay Analysis by Section | Delay reasons tallied by section. |
| Weekly Section MIS | Weekly logs, latest %, open material requests per section. |
| Safety Violations Summary / by Contractor | Violations by section / by contractor. |
| Generator Consumption MIS | Running hours & diesel per generator. |
| Vehicle Utilisation | Trips, hours, distance per site vehicle. |

## The weekly client MIS

The 'Weekly Section MIS' report plus the Benkas MIS dashboard are what you share with Ramshy Bio each week — overall progress, manpower, material and safety at a glance.

# 6.  Ramshy Bio Management — reading the dashboard

You have read-only access to the Benkas MIS dashboard. Open the Benkas ERP tile → Benkas MIS. In one page:

| What you see | What it tells you |
| --- | --- |
| Overall % Complete | Weighted average progress across all 12 sections. |
| Today's Headcount | People on site right now (from gate scans). |
| Open Safety Violations | Unresolved safety issues. |
| Pending Acknowledgements | Gate entries an Incharge hasn't yet confirmed. |
| Headcount by Section chart | Where the workforce is deployed today. |
| Violations by Section chart | Where safety attention is needed. |

Every number traces back to the gate — see the next chapter, 'The daily chain'.

# 7.  The QR system explained

Every ID card and slip carries a QR code. Scanning it is how the plant runs hands-free at the gate.

## What each QR encodes

| Document | QR content | Example |
| --- | --- | --- |
| Staff ID card (Employee) | EMP-<employee id> | EMP-HR-EMP-00001 |
| Labour ID card (Labour Master) | LAB-<labour id> | LAB-LM-00001 |
| Gate Pass slip | GP-<gate pass no> | GP-GP-2026-00012 |
| Visitor slip | VIS-<visitor log no> | VIS-VIS-2026-00034 |

The prefix tells the Scan Station what kind of document it is; the rest is the record's ID. The station reads it and does the right thing automatically.

## Issuing & re-issuing cards

Register the person (Employee or Labour Master), then Print → ID Card. The QR is generated from their record — no manual entry.

Lost/damaged card: just reprint. The QR stays the same because it's tied to their record ID.

Deactivating a Labour (status Inactive/Exited) makes their card fail at the gate immediately — no need to collect the physical card.

## Scanner hardware

Any USB 2D barcode/QR scanner in 'HID keyboard' mode works — it types the code and presses Enter. No drivers, no brand lock-in. This is the primary, fastest path.

A tablet/phone camera also works via the '📷 Camera scan' button (Chrome/Edge, which have the built-in QR reader). Good as a backup or for roaming checks.

Print cards at a size where the QR is ~3 cm — the app already renders them large with error-correction so a smudge or slight angle still scans.

# 8.  The daily chain — from gate to client report

This is how a single scan at the gate becomes a number on the client's weekly report. Anyone can use it to trace any figure back to its source.

① Gate scan  →  Gate Entry (In) with live photo

② Incharge Confirms the entry  →  the person counts as really present

③ Daily Progress Log (Incharge) records: task % + workers + material used

④ On submit  →  Stock Entry auto-issues the material (stock drops)

⑤ Task.progress updates  →  Section % recalculated

⑥ Section % + headcount + material  →  Benkas MIS dashboard

⑦ Weekly Section MIS report  →  shared with Ramshy Bio management

So if management asks 'why is Distillation at 60%?', you trace: dashboard → Section WBS Progress report → the Daily Progress Logs that set those task % → the gate entries and material behind them. Every figure is auditable to a scan and a photo.

# 9.  Troubleshooting & FAQ

| Situation | What to do |
| --- | --- |
| Forgot to scan someone out | Open their Gate Entry and set Time Out manually; or scan the card now. |
| Scanned IN but it says OUT | They already had an open entry today — the scan closed it. Scan once more to open a fresh IN if needed. |
| Photo won't upload / camera blank | Use 'Log IN without photo' to not hold up the queue; check browser camera permission and lighting. |
| Worker not appearing in the Daily Log dropdown | They have no gate entry for your section today. They must be scanned in at the gate first. |
| '…has no gate entry for this section today' | Same as above — the log blocks workers who didn't come through the gate. Scan them in, then add them. |
| Material Request not showing to consume | It must be Approved (not just Requested). Approve it, or check you picked the right section. |
| Section % not updating | Progress comes from the Daily Progress Log's Task Progress rows on submit. Make sure the log was submitted, not left as draft. |
| Stock went negative when submitting a log | The section warehouse has no stock for that item — enter the GRN (Purchase Receipt) first, then log consumption. |
| 'PASS NOT APPROVED' at the gate | The gate pass is still Requested. The person's Incharge must Approve it. |
| Gate pass shows Overdue | It was scanned Out but not scanned back in by the expected time. Find the person; scan Return when they're back. |
| Card says ENTRY BLOCKED | The labour is Inactive/Exited. If that's wrong, the PM sets status back to Active. |
| QR won't scan | Reprint the card larger; clean the scanner window; try the camera-scan button; check the card isn't creased across the QR. |
| Invoice photo blocks my GRN | That's intentional — attach the supplier invoice/challan photo to proceed. |
| Can't close a work permit | Tick the Closing Confirmation (and for electrical, the re-energized sign-off) first. |
| I don't see a workspace/report | Your role doesn't include it. Ask the PM if you should have access. |
| Two people share one card | Never allow it — each person needs their own card so the gate photo and record are theirs. |