RAMSHY BIO PVT. LTD.

Ethanol Plant — Construction Progress

Weekly Management Information Report

Week ending 09 July 2026

Overall completion: 12.5%

11 of 12 sections on track  ·  3.1 person-days this week  ·  1 stopped section-days

Prepared by Benkas Engineering — Project Monitoring Cell

# 1. Project Scorecard

| Metric | Value |
| --- | --- |
| Overall completion | 12.5% |
| Sections on track | 11 of 12 |
| Sections needing attention | 1 |
| Person-days this week | 3.1 |
| Stopped section-days this week | 1 |
| Report window | 03 Jul – 09 Jul 2026 |

# 2. Section-wise Progress

| Code | Section | Incharge | Complete | Status | P-days (wk) | Stopped days |
| --- | --- | --- | --- | --- | --- | --- |
| CO2 | CO2 Plant | — | 0.0% | On Track | 0 | 0 |
| DIST | Distillation Section | Administrator | 38.6% | Attention | 3.1 | 1 |
| DRY | Dryer Section | — | 0.0% | On Track | 0 | 0 |
| ETP | ETP | — | 0.0% | On Track | 0 | 0 |
| EVAP | Evaporation Section | — | 0.0% | On Track | 0 | 0 |
| FERM | Fermentation Section | Administrator | 0.0% | On Track | 0 | 0 |
| LIQ | Liquefaction Section | — | 0.0% | On Track | 0 | 0 |
| MILL | Milling Section | — | 11.4% | On Track | 0 | 0 |
| MSDH | MSDH | — | 0.0% | On Track | 0 | 0 |
| PP | Power Plant | — | 0.0% | On Track | 0 | 0 |
| WHS | Warehouse Stores | — | 100.0% | On Track | 0 | 0 |
| WTP | WTP | — | 0.0% | On Track | 0 | 0 |

# 3. Section Detail

## CO2 — CO2 Plant

Incharge: —   |   0.0% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| CO2 - Civil & Foundation | 0% | Not started |
| CO2 - Commissioning & Verification | 0% | Not started |
| CO2 - Electrical & Wiring | 0% | Not started |
| CO2 - Equipment Installation | 0% | Not started |
| CO2 - Instrumentation & Control | 0% | Not started |
| CO2 - Insulation & Painting | 0% | Not started |
| CO2 - Piping & Fabrication | 0% | Not started |
| CO2 - Structural / Erection | 0% | Not started |
| CO2 - Testing & Inspection | 0% | Not started |

## DIST — Distillation Section

Incharge: Administrator   |   38.6% complete  ·  Attention   |   3.1 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| DIST - Civil & Foundation | 100% | Work Done |
| DIST - Commissioning & Verification | 0% | Not started |
| DIST - Electrical & Wiring | 0% | Not started |
| DIST - Equipment Installation | 100% | Not started |
| DIST - Instrumentation & Control | 0% | Not started |
| DIST - Insulation & Painting | 0% | Not started |
| DIST - Piping & Fabrication | 0% | Not started |
| DIST - Structural / Erection | 60% | Stopped — Rain / Natural Cause |
| DIST - Testing & Inspection | 0% | Not started |

What happened this week:

• 09 Jul [Work Done]: Foundation and civil work fully complete on site.  (100%)

• 09 Jul [Stopped — Rain / Natural Cause]: Heavy rain from noon; erection stopped and columns covered.  (60%)

Stoppages this week:

| Reason | Days |
| --- | --- |
| Stopped — Rain / Natural Cause | 1 |

Material consumed this week:

| Item | Qty | UOM |
| --- | --- | --- |
| BK-CEMENT-OPC53 | 30.0 | Nos |

Photos logged this week (1):

| Task | Date | Caption |
| --- | --- | --- |
| TASK-2026-00077 | 09 Jul | Erection area |

## DRY — Dryer Section

Incharge: —   |   0.0% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| DRY - Civil & Foundation | 0% | Not started |
| DRY - Commissioning & Verification | 0% | Not started |
| DRY - Electrical & Wiring | 0% | Not started |
| DRY - Equipment Installation | 0% | Not started |
| DRY - Instrumentation & Control | 0% | Not started |
| DRY - Insulation & Painting | 0% | Not started |
| DRY - Piping & Fabrication | 0% | Not started |
| DRY - Structural / Erection | 0% | Not started |
| DRY - Testing & Inspection | 0% | Not started |

## ETP — ETP

Incharge: —   |   0.0% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| ETP - Civil & Foundation | 0% | Not started |
| ETP - Commissioning & Verification | 0% | Not started |
| ETP - Electrical & Wiring | 0% | Not started |
| ETP - Equipment Installation | 0% | Not started |
| ETP - Instrumentation & Control | 0% | Not started |
| ETP - Insulation & Painting | 0% | Not started |
| ETP - Piping & Fabrication | 0% | Not started |
| ETP - Structural / Erection | 0% | Not started |
| ETP - Testing & Inspection | 0% | Not started |

## EVAP — Evaporation Section

Incharge: —   |   0.0% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| EVAP - Civil & Foundation | 0% | Not started |
| EVAP - Commissioning & Verification | 0% | Not started |
| EVAP - Electrical & Wiring | 0% | Not started |
| EVAP - Equipment Installation | 0% | Not started |
| EVAP - Instrumentation & Control | 0% | Not started |
| EVAP - Insulation & Painting | 0% | Not started |
| EVAP - Piping & Fabrication | 0% | Not started |
| EVAP - Structural / Erection | 0% | Not started |
| EVAP - Testing & Inspection | 0% | Not started |

## FERM — Fermentation Section

Incharge: Administrator   |   0.0% complete  ·  On Track   |   0 person-days this week   |   1 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| FERM - Civil & Foundation | 80% | Not started |
| FERM - Commissioning & Verification | 0% | Not started |
| FERM - Electrical & Wiring | 0% | Not started |
| FERM - Equipment Installation | 0% | Not started |
| FERM - Instrumentation & Control | 0% | Not started |
| FERM - Insulation & Painting | 0% | Not started |
| FERM - Piping & Fabrication | 0% | Not started |
| FERM - Structural / Erection | 0% | Not started |
| FERM - Testing & Inspection | 0% | Not started |

## LIQ — Liquefaction Section

Incharge: —   |   0.0% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| LIQ - Civil & Foundation | 0% | Not started |
| LIQ - Commissioning & Verification | 0% | Not started |
| LIQ - Electrical & Wiring | 0% | Not started |
| LIQ - Equipment Installation | 0% | Not started |
| LIQ - Instrumentation & Control | 0% | Not started |
| LIQ - Insulation & Painting | 0% | Not started |
| LIQ - Piping & Fabrication | 0% | Not started |
| LIQ - Structural / Erection | 0% | Not started |
| LIQ - Testing & Inspection | 0% | Not started |

## MILL — Milling Section

Incharge: —   |   11.4% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| MILL - Civil & Foundation | 70% | Not started |
| MILL - Commissioning & Verification | 0% | Not started |
| MILL - Electrical & Wiring | 0% | Not started |
| MILL - Equipment Installation | 0% | Not started |
| MILL - Instrumentation & Control | 0% | Not started |
| MILL - Insulation & Painting | 0% | Not started |
| MILL - Piping & Fabrication | 0% | Not started |
| MILL - Structural / Erection | 20% | Not started |
| MILL - Testing & Inspection | 0% | Not started |

## MSDH — MSDH

Incharge: —   |   0.0% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| MSDH - Civil & Foundation | 0% | Not started |
| MSDH - Commissioning & Verification | 0% | Not started |
| MSDH - Electrical & Wiring | 0% | Not started |
| MSDH - Equipment Installation | 0% | Not started |
| MSDH - Instrumentation & Control | 0% | Not started |
| MSDH - Insulation & Painting | 0% | Not started |
| MSDH - Piping & Fabrication | 0% | Not started |
| MSDH - Structural / Erection | 0% | Not started |
| MSDH - Testing & Inspection | 0% | Not started |

## PP — Power Plant

Incharge: —   |   0.0% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| PP - Civil & Foundation | 0% | Not started |
| PP - Commissioning & Verification | 0% | Not started |
| PP - Electrical & Wiring | 0% | Not started |
| PP - Equipment Installation | 0% | Not started |
| PP - Instrumentation & Control | 0% | Not started |
| PP - Insulation & Painting | 0% | Not started |
| PP - Piping & Fabrication | 0% | Not started |
| PP - Structural / Erection | 0% | Not started |
| PP - Testing & Inspection | 0% | Not started |

## WHS — Warehouse Stores

Incharge: —   |   100.0% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| WHS - Civil & Foundation | 100% | Not started |
| WHS - Commissioning & Verification | 100% | Not started |
| WHS - Electrical & Wiring | 100% | Not started |
| WHS - Equipment Installation | 100% | Not started |
| WHS - Instrumentation & Control | 100% | Not started |
| WHS - Insulation & Painting | 100% | Not started |
| WHS - Piping & Fabrication | 100% | Not started |
| WHS - Structural / Erection | 100% | Not started |
| WHS - Testing & Inspection | 100% | Not started |

## WTP — WTP

Incharge: —   |   0.0% complete  ·  On Track   |   0 person-days this week   |   0 visitor(s)

| Task | % Complete | Latest Status |
| --- | --- | --- |
| WTP - Civil & Foundation | 0% | Not started |
| WTP - Commissioning & Verification | 0% | Not started |
| WTP - Electrical & Wiring | 0% | Not started |
| WTP - Equipment Installation | 0% | Not started |
| WTP - Instrumentation & Control | 0% | Not started |
| WTP - Insulation & Painting | 0% | Not started |
| WTP - Piping & Fabrication | 0% | Not started |
| WTP - Structural / Erection | 0% | Not started |
| WTP - Testing & Inspection | 0% | Not started |

# 4. Manpower Annex (this week)

Person-days by contractor / team

| Contractor / Team | Person-days |
| --- | --- |
| Sri Sai Constructions | 2.1 |
| Employee | 1.0 |

Person-days by category

| Category | Person-days |
| --- | --- |
| Labour Master | 2.1 |
| Employee | 1.0 |

# 5. Material Annex (this week)

Material received (by section)

| Section | Value received |
| --- | --- |
| Nothing received |  |

Material issued to work (by section)

| Section | Value issued |
| --- | --- |
| DIST | ₹ 0.00 |

# 6. Stoppages & Attention Required

Stopped section-days by reason (whole project)

| Reason | Section-days |
| --- | --- |
| Stopped — Rain / Natural Cause | 1 |

Open safety violations

| Section | Type | Person | When |
| --- | --- | --- | --- |
| DIST | No Helmet | LM-00002 | 06 Jul |

Overdue gate passes (tools/material not returned)

| Gate Pass | Person | Expected Return |
| --- | --- | --- |
| None |  |  |

— End of report —  Generated by Benkas ERP on 09 Jul 2026